## PAGE_1
Design & Build Works for Lusail Plaza Towers - Plot 1 (BP12A) & Plot 2 BP12B
Testing & Commissioning Procedure for TAB of HVAC Equipment
PROJECT | : | Design & Build Works for Lusail Plaza Towers
SERVED | : | level-01 | [8 empty] | TAC Ref. |  |  | :
LOCATION | : | tower-1 | [8 empty] | ITP Ref. |  |  | :
SYSTEM | : | [9 empty] | Drawing No. |  |  | :
SPACE TEMPERATURE DATA
HVAC SYSTEM |  |  |  | AMBIENT AIR TEMP |  |  | ROOM | THERMOSTAT SET POINT ºc |  | DESIGN |  |  |  |  | INDOOR READINGS | [6 empty] | REMARKS
|  |  |  | DB | WB |  |  |  |  | TEMP |  |  | %RH |  | TIME |  | DB | WB |  | %RH
fcu-01 |  |  |  | 47 | 23 |  | testing | 22 |  | 44/55 |  |  |  |  | 10:20 |  | 23 | 12 |  | 45 |  | testing
REMARKS : |  |  | Pass |  |  |  | Fail |  | Tested Date |  |  |  | :
N.S. = NOT SPECIFIED / N.A = NOT APPLICABLE
Instrument Used: |  |  |  |  | Make / Model : | [5 empty] | Serial No : | [6 empty] | Calibration Due :
THERMO HYGROMETER |  |  |  |  | TSI / 7451 | [5 empty] | T74151148001 | [6 empty] | 2027-04-26
Approved |  |  |  |  | Approved With Comments | [6 empty] | Revise and Resubmit | [6 empty] | Rejected
|  | Tested by: | [6 empty] | Witnessed by: | [11 empty] | Approved by:
|  | AJB TAB Engineer |  |  |  | MMJV Engineer |  |  | MMJV T&C Engineer | [6 empty] | CxA |  |  |  |  | Consultant
Name:
Sign & Date:
Designation:
562QLT-BP12-MMJV-PRC-ME-CKL-00030-N_Rev.002-TAB- Test Report for Space Temperature